## Sprint 1 Backlog
Story # | Sprint Backlog Item | Task # | Volunteer | Task Details | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of | [5 empty] | Status
[6 empty] | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
US001 | cashier and his backend work is the sprint backlog | Task 1 | santhosh | create database models | 3 | New Estimates of Effort remaining at end of Day1: 1; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 2 | jinto josan | write program for the home page and create skeleton | 5 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 3 | santhosh | Design and create the DB fields and manage scrum sheets | 3 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 4 | jinto josan | write login session and and home page ui | 3 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 5 | santhosh | write ui and backend for customer creation , update and delete | 6 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | task 6 | jinto josan | write ui and backend for account creation and delete | 5 | New Estimates of Effort remaining at end of Day1: 2 | Closed
|  | task7 | santhosh | Execute the tests and version control | 2 | New Estimates of Effort remaining at end of Day1: 0 | Closed
US002 | css and other decorations at ui | Task 1 | santhosh | write code for transaction and develop ui for it | 6 | New Estimates of Effort remaining at end of Day1: 4; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 2 | jinto josan | write code for ui and login for home layout of cashier | 6 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 3 | santhosh | test code of transactions | 2 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 4 | jinto josan | write code for status of accounts | 5 | New Estimates of Effort remaining at end of Day1: 1; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | task 5 | santhosh | test and merge code for cashier layout and transactions | 3 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | task 6 | jinto josan | handle login and logout session token | 5 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
US003 | end to end test | task 1 | santhosh | prettify all the developed pages and test end to end | 5 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | in progress
|  | task 2 | jinto josan | prettify all the developed pages and test end to end | 5 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | in progress
|  |  |  | Total | 64 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0

## Sprint 1 Burndown Chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
300 | 260 | 220 | 160 | 90 | 65 | 0
300 | 250 | 200 | 150 | 100 | 50 | 0